## Sheet3
Expected Results | Expected Results2 | Status | Status By | Status Comment
- The list reports should be exportable in formats such as CSV, xlsx or pdf | Can export the different report list to a portable format such as CSV/XLSX/XLS or pdf | Ongoing |  | - Need for additional formats such as XLS/XLSX/PDF
- report lists with filters for different fields on the different system items, e.g calls, cases and performance | Show different item list reports such as cases and calls. The list report can be filtered based on relevant report parameters | Ongoing |  | - Some report filters are not fully working - Need for additional fields on some report filters
- Users notified on case updates | Users who have interacted with a case receive notification when the case is updated | Ongoing |  | - Not received notifications on case update though there is a notification tab
- Capture necessary fields for respective groupings in the case Capture form | All the fields for case form should be listed as per the FRD | Ongoing |  | - Locations and Categories should be in different hierarchical fields - Act on the shared iput fields
- A information page with details such as: - Helpline services - Helpline FAQs - An option to create case - General helpline statistics - Calls and cases by location, type (VAC/GBV), categories and date | Web page created with relevant information as defined in the requirements | Ongoing
- Type options such as New Case, Follow Up, Counselling and Information inquiry | Being able to select reason for calling as either Follow Up, Counselling, Information Inquiry or New Case | Ongoing |  | - Have the forms for Counselling and Information & Inquiry
- Dashboard statistics filtering | Can filter statistics based on different parameters such as timeframe | Ongoing
- Segregate cases in groupings such as New, Escalated and/or All Cases - View individual cases with a printable version or exportable to PDF | View individual case with all the captured details | Ongoing |  | - list escalated cases ordered by date escalated - Print the case under case view/export to pdf
- provide filters for case list to allow for ease in case search | Search and/or filter a cases by different fields | Ongoing |  | - Not all fields work - add client name, escalation date, client location - for case category, use only main categories
- Dashboards relevant to the different user roles | Every user level presents a dashboard with relevant user statistics and data to the role | Ongoing |  | - Users do not currently have call & case statistics - administrators should see statisticsforthe entire system
- Call lists shall be listed with filters available for a user to search | When a user searches/filters the cal list, it should return relevant results based on the selected parameter fields | Ongoing |  | - Work on list filters - provide an exit button for the filter form
- Call transfer/conference/invite | One is able to transfer a call to another registered user | Ongoing
Users can view listing of cases escalated to them and/or the cases they escalate to other users | Can view cases escalated in/out | Ongoing
- A case/call disposition available all through a call/case capture | Can dispose a case at any level and record the reason for disposing the case. | Ongoing
- maintain a history of case edits | Keep current record and keep the previous details upon case edit | Ongoing

## Sheet5
Expected Results | Expected Results2 | Status | Status By | Status Comment
- The list reports should be exportable in formats such as CSV, xlsx or pdf | Can export the different report list to a portable format such as CSV/XLSX/XLS or pdf | Ongoing |  | - Need for additional formats such as XLS/XLSX/PDF
- report lists with filters for different fields on the different system items, e.g calls, cases and performance | Show different item list reports such as cases and calls. The list report can be filtered based on relevant report parameters | Ongoing |  | - Some report filters are not fully working - Need for additional fields on some report filters
- Users notified on case updates | Users who have interacted with a case receive notification when the case is updated | Ongoing |  | - Not received notifications on case update though there is a notification tab
- Capture necessary fields for respective groupings in the case Capture form | All the fields for case form should be listed as per the FRD | Ongoing |  | - Locations and Categories should be in different hierarchical fields - Act on the shared iput fields
- A information page with details such as: - Helpline services - Helpline FAQs - An option to create case - General helpline statistics - Calls and cases by location, type (VAC/GBV), categories and date | Web page created with relevant information as defined in the requirements | Ongoing
- Type options such as New Case, Follow Up, Counselling and Information inquiry | Being able to select reason for calling as either Follow Up, Counselling, Information Inquiry or New Case | Ongoing |  | - Have the forms for Counselling and Information & Inquiry
- Dashboard statistics filtering | Can filter statistics based on different parameters such as timeframe | Ongoing
- Segregate cases in groupings such as New, Escalated and/or All Cases - View individual cases with a printable version or exportable to PDF | View individual case with all the captured details | Ongoing |  | - list escalated cases ordered by date escalated - Print the case under case view/export to pdf
- provide filters for case list to allow for ease in case search | Search and/or filter a cases by different fields | Ongoing |  | - Not all fields work - add client name, escalation date, client location - for case category, use only main categories
- Dashboards relevant to the different user roles | Every user level presents a dashboard with relevant user statistics and data to the role | Ongoing |  | - Users do not currently have call & case statistics - administrators should see statisticsforthe entire system
- Call lists shall be listed with filters available for a user to search | When a user searches/filters the cal list, it should return relevant results based on the selected parameter fields | Ongoing |  | - Work on list filters - provide an exit button for the filter form
- Call transfer/conference/invite | One is able to transfer a call to another registered user | Ongoing
Users can view listing of cases escalated to them and/or the cases they escalate to other users | Can view cases escalated in/out | Ongoing
- A case/call disposition available all through a call/case capture | Can dispose a case at any level and record the reason for disposing the case. | Ongoing
- maintain a history of case edits | Keep current record and keep the previous details upon case edit | Ongoing

## Sheet6
Expected Results | Expected Results2 | Status | Status By | Status Comment
- Ability to create a case successfully | Web online form can submit a case to the system | Not Done
- Web form with relevant fields | A case form on the web page with the defined fields | Not Done
| Wall dashboard that shows center statistics and real time user activities | Not Done
- a report of system users, their current status and respective statistics | A supervisor should view the status of currently logged in users and their queue & activity status | Not Done |  | - Add to supervisor and Administrator account
- Change personal password | Each logged-in user can change their own password | Not Done
- call budging, listening and/or whispering | Ability to have and perform the listed options for assistance and/or QA during call | Not Done
Form and data capture | - capture end to end information on counselling as offered to a client | Not Done
Update on FAQs | Create new questions for FAQs | Not Done
Form and data capture | - View information of importance in responding to client queries | Not Done
inf

## Dashboard
Status | Count of Status
Done | 26
Not Done | 9
Not Tested | 5
Ongoing | 14
Grand Total | 54

## Detail3
Expected Results | Expected Results | Status | Status By | Status Comment
- Can login successfully - Warnings on wrong credentials | Being able to login and receive error messages if the login is not successful | Done
- redirection to the right dashboard and role | Every user logged in should be redirected to the respective dashboard with details filtered per user level | Done
- Capture necessary fields for respective groupings in the case Capture form | All the fields for case form should be listed as per the FRD | Ongoing |  | - Locations and Categories should be in different hierarchical fields - Act on the shared iput fields
- case form logic and flow | Step by step capture of case details from case reporter to case closure | Done
- Type options such as New Case, Follow Up, Counselling and Information inquiry | Being able to select reason for calling as either Follow Up, Counselling, Information Inquiry or New Case | Ongoing |  | - Have the forms for Counselling and Information & Inquiry
- Being able to edit a case with respective logic in mind | Ability to update case | Done
- Segregate cases in groupings such as New, Escalated and/or All Cases - View individual cases with a printable version or exportable to PDF | View individual case with all the captured details | Ongoing |  | - list escalated cases ordered by date escalated - Print the case under case view/export to pdf
- provide filters for case list to allow for ease in case search | Search and/or filter a cases by different fields | Ongoing |  | - Not all fields work - add client name, escalation date, client location - for case category, use only main categories
- Counsellors and supervisors being able to escalate cases and view where possible | A case can be escalated by a counsellor and supervisor | Done
- case managers being able to assign a case to case workers - Define escalation matrix based on current logged in user | Assign/assign case to Case Workers by Case Managers | Done
Users can view listing of cases escalated to them and/or the cases they escalate to other users | Can view cases escalated in/out | Ongoing
- Every case should have a unique case number | Cases created to have a unique case number to identify it. | Done
- Every case should have a source | Each case is tagged to a source | Done
- maintain a history of case edits | Keep current record and keep the previous details upon case edit | Ongoing
- A case can be escalated in the following steps: Counsellor => Supervisor => Case Manager => Case Worker | Counsellor, Supervisor and Caseworker can escalate a case to the next user level | Done
- A case/call disposition available all through a call/case capture | Can dispose a case at any level and record the reason for disposing the case. | Ongoing
Form and data capture | - View information of importance in responding to client queries | Not Done
Update on FAQs | Create new questions for FAQs | Not Done
Form and data capture | - capture end to end information on counselling as offered to a client | Not Done
- SIP setup | Having a setup for SIP phone to receive and make calls | Done
- Inbound calls | Being able to receive calls on a SIP phone | Done
- SIP to SIP calls | Ability to make calls between registered system users | Done
- SIP Extension management | Assigning extension numbers to users | Done |  | Automate the numbering
- Form popup on call received | Case form should pop for external inbound calls upon receiving | Done
- Call transfer/conference/invite | One is able to transfer a call to another registered user | Ongoing
- Join and leave queue | A user can join and leave queue. One should not receive calls when not in queue and vice versa | Done
- call budging, listening and/or whispering | Ability to have and perform the listed options for assistance and/or QA during call | Not Done
- IVR configurations and provisions | Ability to add IVR audio to the system and reflect on inbound calls | Not Tested
- Call lists shall be listed with filters available for a user to search | When a user searches/filters the cal list, it should return relevant results based on the selected parameter fields | Ongoing |  | - Work on list filters - provide an exit button for the filter form
- QA form with respective fields and saving | Have a form for relevant QA fields which can be submitted and saves awarded points | Done
- Qa form having audio player for the respective call record with controls | The QA form that pops for a call should have an audio player that plays the respective relevant audio upon loading. It should have controls for pausing and rewinding | Done
- Listing should allow supervisor to search for a particular call | Being able to filter call listing for QA to find a relevant call for analysis | Done |  | - Filter not available or not working
- Results from a quality analysis | One should be able to view the results of a QA as submitted by a supervisor | Done
- User creation | User can be created and s/he can login successfully | Done
- User update | User details can be updated relevantly | Done
- Users levels/role separation - Administrator - Partner - Case Manager - Case Worker - Counsellor - Supervisor | - The user levels exist within the system and available during user creation | Done |  | - Add partner to the levels and test
- Change personal password | Each logged-in user can change their own password | Not Done
- Change user password for administrators | Administrators can reset user password | Done
- Different user roles and role separation within the system as defined | - The different user roles to have distinctive role &separation | Done
- a report of system users, their current status and respective statistics | A supervisor should view the status of currently logged in users and their queue & activity status | Not Done |  | - Add to supervisor and Administrator account
- Dashboards relevant to the different user roles | Every user level presents a dashboard with relevant user statistics and data to the role | Ongoing |  | - Users do not currently have call & case statistics - administrators should see statisticsforthe entire system
- Dashboard statistics filtering | Can filter statistics based on different parameters such as timeframe | Ongoing
| Wall dashboard that shows center statistics and real time user activities | Not Done
- A information page with details such as: - Helpline services - Helpline FAQs - An option to create case - General helpline statistics - Calls and cases by location, type (VAC/GBV), categories and date | Web page created with relevant information as defined in the requirements | Ongoing
- Web form with relevant fields | A case form on the web page with the defined fields | Not Done
- Ability to create a case successfully | Web online form can submit a case to the system | Not Done
- web created cased listing on the CRM | The submitted cases from web online form are listed on the local system | Not Tested
- Creating a system case with a web online listing | The case from web online can be used to create a case on the system | Not Tested
- Users notified on case updates | Users who have interacted with a case receive notification when the case is updated | Ongoing |  | - Not received notifications on case update though there is a notification tab
- Users notified on new/unread SMS | Users get a notification on an incoming SMS | Not Tested
- Users notified on new/unread emails | Users get a notification on an incoming Email | Not Tested
- report lists with filters for different fields on the different system items, e.g calls, cases and performance | Show different item list reports such as cases and calls. The list report can be filtered based on relevant report parameters | Ongoing |  | - Some report filters are not fully working - Need for additional fields on some report filters
- The list reports should be exportable in formats such as CSV, xlsx or pdf | Can export the different report list to a portable format such as CSV/XLSX/XLS or pdf | Ongoing |  | - Need for additional formats such as XLS/XLSX/PDF
- Custom pivoted reports for both calls and cases having graphical and statistical representaion. | Can do custom pivot reports | Done

## Detail2
Expected Results | Expected Results | Status | Status By | Status Comment
- Can login successfully - Warnings on wrong credentials | Being able to login and receive error messages if the login is not successful | Done
- redirection to the right dashboard and role | Every user logged in should be redirected to the respective dashboard with details filtered per user level | Done
- Capture necessary fields for respective groupings in the case Capture form | All the fields for case form should be listed as per the FRD | Ongoing |  | - Locations and Categories should be in different hierarchical fields - Act on the shared iput fields
- case form logic and flow | Step by step capture of case details from case reporter to case closure | Done
- Type options such as New Case, Follow Up, Counselling and Information inquiry | Being able to select reason for calling as either Follow Up, Counselling, Information Inquiry or New Case | Ongoing |  | - Have the forms for Counselling and Information & Inquiry
- Being able to edit a case with respective logic in mind | Ability to update case | Done
- Segregate cases in groupings such as New, Escalated and/or All Cases - View individual cases with a printable version or exportable to PDF | View individual case with all the captured details | Ongoing |  | - list escalated cases ordered by date escalated - Print the case under case view/export to pdf
- provide filters for case list to allow for ease in case search | Search and/or filter a cases by different fields | Ongoing |  | - Not all fields work - add client name, escalation date, client location - for case category, use only main categories
- Counsellors and supervisors being able to escalate cases and view where possible | A case can be escalated by a counsellor and supervisor | Done
- case managers being able to assign a case to case workers - Define escalation matrix based on current logged in user | Assign/assign case to Case Workers by Case Managers | Done
Users can view listing of cases escalated to them and/or the cases they escalate to other users | Can view cases escalated in/out | Ongoing
- Every case should have a unique case number | Cases created to have a unique case number to identify it. | Done
- Every case should have a source | Each case is tagged to a source | Done
- maintain a history of case edits | Keep current record and keep the previous details upon case edit | Ongoing
- A case can be escalated in the following steps: Counsellor => Supervisor => Case Manager => Case Worker | Counsellor, Supervisor and Caseworker can escalate a case to the next user level | Done
- A case/call disposition available all through a call/case capture | Can dispose a case at any level and record the reason for disposing the case. | Ongoing
Form and data capture | - View information of importance in responding to client queries | Not Done
Update on FAQs | Create new questions for FAQs | Not Done
Form and data capture | - capture end to end information on counselling as offered to a client | Not Done
- SIP setup | Having a setup for SIP phone to receive and make calls | Done
- Inbound calls | Being able to receive calls on a SIP phone | Done
- SIP to SIP calls | Ability to make calls between registered system users | Done
- SIP Extension management | Assigning extension numbers to users | Done |  | Automate the numbering
- Form popup on call received | Case form should pop for external inbound calls upon receiving | Done
- Call transfer/conference/invite | One is able to transfer a call to another registered user | Ongoing
- Join and leave queue | A user can join and leave queue. One should not receive calls when not in queue and vice versa | Done
- call budging, listening and/or whispering | Ability to have and perform the listed options for assistance and/or QA during call | Not Done
- IVR configurations and provisions | Ability to add IVR audio to the system and reflect on inbound calls | Not Tested
- Call lists shall be listed with filters available for a user to search | When a user searches/filters the cal list, it should return relevant results based on the selected parameter fields | Ongoing |  | - Work on list filters - provide an exit button for the filter form
- QA form with respective fields and saving | Have a form for relevant QA fields which can be submitted and saves awarded points | Done
- Qa form having audio player for the respective call record with controls | The QA form that pops for a call should have an audio player that plays the respective relevant audio upon loading. It should have controls for pausing and rewinding | Done
- Listing should allow supervisor to search for a particular call | Being able to filter call listing for QA to find a relevant call for analysis | Done |  | - Filter not available or not working
- Results from a quality analysis | One should be able to view the results of a QA as submitted by a supervisor | Done
- User creation | User can be created and s/he can login successfully | Done
- User update | User details can be updated relevantly | Done
- Users levels/role separation - Administrator - Partner - Case Manager - Case Worker - Counsellor - Supervisor | - The user levels exist within the system and available during user creation | Done |  | - Add partner to the levels and test
- Change personal password | Each logged-in user can change their own password | Not Done
- Change user password for administrators | Administrators can reset user password | Done
- Different user roles and role separation within the system as defined | - The different user roles to have distinctive role &separation | Done
- a report of system users, their current status and respective statistics | A supervisor should view the status of currently logged in users and their queue & activity status | Not Done |  | - Add to supervisor and Administrator account
- Dashboards relevant to the different user roles | Every user level presents a dashboard with relevant user statistics and data to the role | Ongoing |  | - Users do not currently have call & case statistics - administrators should see statisticsforthe entire system
- Dashboard statistics filtering | Can filter statistics based on different parameters such as timeframe | Ongoing
| Wall dashboard that shows center statistics and real time user activities | Not Done
- A information page with details such as: - Helpline services - Helpline FAQs - An option to create case - General helpline statistics - Calls and cases by location, type (VAC/GBV), categories and date | Web page created with relevant information as defined in the requirements | Ongoing
- Web form with relevant fields | A case form on the web page with the defined fields | Not Done
- Ability to create a case successfully | Web online form can submit a case to the system | Not Done
- web created cased listing on the CRM | The submitted cases from web online form are listed on the local system | Not Tested
- Creating a system case with a web online listing | The case from web online can be used to create a case on the system | Not Tested
- Users notified on case updates | Users who have interacted with a case receive notification when the case is updated | Ongoing |  | - Not received notifications on case update though there is a notification tab
- Users notified on new/unread SMS | Users get a notification on an incoming SMS | Not Tested
- Users notified on new/unread emails | Users get a notification on an incoming Email | Not Tested
- report lists with filters for different fields on the different system items, e.g calls, cases and performance | Show different item list reports such as cases and calls. The list report can be filtered based on relevant report parameters | Ongoing |  | - Some report filters are not fully working - Need for additional fields on some report filters
- The list reports should be exportable in formats such as CSV, xlsx or pdf | Can export the different report list to a portable format such as CSV/XLSX/XLS or pdf | Ongoing |  | - Need for additional formats such as XLS/XLSX/PDF
- Custom pivoted reports for both calls and cases having graphical and statistical representaion. | Can do custom pivot reports | Done

## Detail1
| Expected Results | Status | Status By | Status Comment
- Can login successfully - Warnings on wrong credentials | Being able to login and receive error messages if the login is not successful | Done
- redirection to the right dashboard and role | Every user logged in should be redirected to the respective dashboard with details filtered per user level | Done
- Capture necessary fields for respective groupings in the case Capture form | All the fields for case form should be listed as per the FRD | Ongoing |  | - Locations and Categories should be in different hierarchical fields - Act on the shared iput fields
- case form logic and flow | Step by step capture of case details from case reporter to case closure | Done
- Type options such as New Case, Follow Up, Counselling and Information inquiry | Being able to select reason for calling as either Follow Up, Counselling, Information Inquiry or New Case | Ongoing |  | - Have the forms for Counselling and Information & Inquiry
- Being able to edit a case with respective logic in mind | Ability to update case | Done
- Segregate cases in groupings such as New, Escalated and/or All Cases - View individual cases with a printable version or exportable to PDF | View individual case with all the captured details | Ongoing |  | - list escalated cases ordered by date escalated - Print the case under case view/export to pdf
- provide filters for case list to allow for ease in case search | Search and/or filter a cases by different fields | Ongoing |  | - Not all fields work - add client name, escalation date, client location - for case category, use only main categories
- Counsellors and supervisors being able to escalate cases and view where possible | A case can be escalated by a counsellor and supervisor | Done
- case managers being able to assign a case to case workers - Define escalation matrix based on current logged in user | Assign/assign case to Case Workers by Case Managers | Done
Users can view listing of cases escalated to them and/or the cases they escalate to other users | Can view cases escalated in/out | Ongoing
- Every case should have a unique case number | Cases created to have a unique case number to identify it. | Done
- Every case should have a source | Each case is tagged to a source | Done
- maintain a history of case edits | Keep current record and keep the previous details upon case edit | Ongoing
- A case can be escalated in the following steps: Counsellor => Supervisor => Case Manager => Case Worker | Counsellor, Supervisor and Caseworker can escalate a case to the next user level | Done
- A case/call disposition available all through a call/case capture | Can dispose a case at any level and record the reason for disposing the case. | Ongoing
Form and data capture | - View information of importance in responding to client queries | Not Done
Update on FAQs | Create new questions for FAQs | Not Done
Form and data capture | - capture end to end information on counselling as offered to a client | Not Done
- SIP setup | Having a setup for SIP phone to receive and make calls | Done
- Inbound calls | Being able to receive calls on a SIP phone | Done
- SIP to SIP calls | Ability to make calls between registered system users | Done
- SIP Extension management | Assigning extension numbers to users | Done |  | Automate the numbering
- Form popup on call received | Case form should pop for external inbound calls upon receiving | Done
- Call transfer/conference/invite | One is able to transfer a call to another registered user | Ongoing
- Join and leave queue | A user can join and leave queue. One should not receive calls when not in queue and vice versa | Done
- call budging, listening and/or whispering | Ability to have and perform the listed options for assistance and/or QA during call | Not Done
- IVR configurations and provisions | Ability to add IVR audio to the system and reflect on inbound calls | Not Tested
- Call lists shall be listed with filters available for a user to search | When a user searches/filters the cal list, it should return relevant results based on the selected parameter fields | Ongoing |  | - Work on list filters - provide an exit button for the filter form
- QA form with respective fields and saving | Have a form for relevant QA fields which can be submitted and saves awarded points | Done
- Qa form having audio player for the respective call record with controls | The QA form that pops for a call should have an audio player that plays the respective relevant audio upon loading. It should have controls for pausing and rewinding | Done
- Listing should allow supervisor to search for a particular call | Being able to filter call listing for QA to find a relevant call for analysis | Done |  | - Filter not available or not working
- Results from a quality analysis | One should be able to view the results of a QA as submitted by a supervisor | Done
- User creation | User can be created and s/he can login successfully | Done
- User update | User details can be updated relevantly | Done
- Users levels/role separation - Administrator - Partner - Case Manager - Case Worker - Counsellor - Supervisor | - The user levels exist within the system and available during user creation | Done |  | - Add partner to the levels and test
- Change personal password | Each logged-in user can change their own password | Not Done
- Change user password for administrators | Administrators can reset user password | Done
- Different user roles and role separation within the system as defined | - The different user roles to have distinctive role &separation | Done
- a report of system users, their current status and respective statistics | A supervisor should view the status of currently logged in users and their queue & activity status | Not Done |  | - Add to supervisor and Administrator account
- Dashboards relevant to the different user roles | Every user level presents a dashboard with relevant user statistics and data to the role | Ongoing |  | - Users do not currently have call & case statistics - administrators should see statisticsforthe entire system
- Dashboard statistics filtering | Can filter statistics based on different parameters such as timeframe | Ongoing
| Wall dashboard that shows center statistics and real time user activities | Not Done
- A information page with details such as: - Helpline services - Helpline FAQs - An option to create case - General helpline statistics - Calls and cases by location, type (VAC/GBV), categories and date | Web page created with relevant information as defined in the requirements | Ongoing
- Web form with relevant fields | A case form on the web page with the defined fields | Not Done
- Ability to create a case successfully | Web online form can submit a case to the system | Not Done
- web created cased listing on the CRM | The submitted cases from web online form are listed on the local system | Not Tested
- Creating a system case with a web online listing | The case from web online can be used to create a case on the system | Not Tested
- Users notified on case updates | Users who have interacted with a case receive notification when the case is updated | Ongoing |  | - Not received notifications on case update though there is a notification tab
- Users notified on new/unread SMS | Users get a notification on an incoming SMS | Not Tested
- Users notified on new/unread emails | Users get a notification on an incoming Email | Not Tested
- report lists with filters for different fields on the different system items, e.g calls, cases and performance | Show different item list reports such as cases and calls. The list report can be filtered based on relevant report parameters | Ongoing |  | - Some report filters are not fully working - Need for additional fields on some report filters
- The list reports should be exportable in formats such as CSV, xlsx or pdf | Can export the different report list to a portable format such as CSV/XLSX/XLS or pdf | Ongoing |  | - Need for additional formats such as XLS/XLSX/PDF
- Custom pivoted reports for both calls and cases having graphical and statistical representaion. | Can do custom pivot reports | Done

## Phase I
UCHL VAC/GBV Upgrade System Feature Sign-Off Checklist
Module | Module | Item | Expected Results | Expected Results | Status | Status By | Status Comment | Priority
Phase I
| User Login | Login Process | - Can login successfully - Warnings on wrong credentials | Being able to login and receive error messages if the login is not successful | Done
|  |  | - redirection to the right dashboard and role | Every user logged in should be redirected to the respective dashboard with details filtered per user level | Done |  |  |  |  | Priority Key
| Case Management | Case creation | - Capture necessary fields for respective groupings in the case Capture form | All the fields for case form should be listed as per the FRD | Ongoing |  | - Locations and Categories should be in different hierarchical fields - Act on the shared iput fields |  | Done |  | High Priority
|  |  | - case form logic and flow | Step by step capture of case details from case reporter to case closure | Done |  |  |  | Ongoing |  | Medium Priority
|  |  | - Type options such as New Case, Follow Up, Counselling and Information inquiry | Being able to select reason for calling as either Follow Up, Counselling, Information Inquiry or New Case | Done |  | - Have the forms for Counselling and Information & Inquiry |  | Not Tested |  | Low Priority
|  | Case edit | - Being able to edit a case with respective logic in mind | Ability to update case | Done |  |  |  | Pending
|  | Case View | - Segregate cases in groupings such as New, Escalated and/or All Cases - View individual cases with a printable version or exportable to PDF | View individual case with all the captured details | Ongoing |  | - list escalated cases ordered by date escalated - Print the case under case view/export to pdf |  | Not Done
|  |  | - provide filters for case list to allow for ease in case search | Search and/or filter a cases by different fields | Ongoing |  | - Not all fields work - add client name, escalation date, client location - for case category, use only main categories
|  |  |  | Viewed case to have an option to edit | Dropped |  | Repeated |  | Dropped
|  | Case escalation and assignment | - Counsellors and supervisors being able to escalate cases and view where possible | A case can be escalated by a counsellor and supervisor | Done
|  |  | - case managers being able to assign a case to case workers - Define escalation matrix based on current logged in user | Assign/assign case to Case Workers by Case Managers | Done
|  |  | Users can view listing of cases escalated to them and/or the cases they escalate to other users | Can view cases escalated in/out | Ongoing
|  | Case identification | - Every case should have a unique case number | Cases created to have a unique case number to identify it. | Done
|  |  | - Every case should have a source | Each case is tagged to a source | Done
|  | Case Trail | - maintain a history of case edits | Keep current record and keep the previous details upon case edit | Ongoing
|  | Escalation matrix | - A case can be escalated in the following steps: Counsellor => Supervisor => Case Manager => Case Worker | Counsellor, Supervisor and Caseworker can escalate a case to the next user level | Done
|  | Case/call Disposition | - A case/call disposition available all through a call/case capture | Can dispose a case at any level and record the reason for disposing the case. | Ongoing
| Information Inquiry/Service Forms | Information Inquiry | Form and data capture | - View information of importance in responding to client queries | Not Done
|  |  | Update on FAQs | Create new questions for FAQs | Not Done
|  | Counselling | Form and data capture | - capture end to end information on counselling as offered to a client | Not Done
| Call Management | SIP Phone setup & configuration | - SIP setup | Having a setup for SIP phone to receive and make calls | Done
|  |  | - Inbound calls | Being able to receive calls on a SIP phone | Done
|  |  | - SIP to SIP calls | Ability to make calls between registered system users | Done
|  |  | - SIP Extension management | Assigning extension numbers to users | Done |  | Automate the numbering
|  |  | - Form popup on call received | Case form should pop for external inbound calls upon receiving | Done
|  |  | - Call transfer/conference/invite | One is able to transfer a call to another registered user | Ongoing
|  | Call Queue Management | - Join and leave queue | A user can join and leave queue. One should not receive calls when not in queue and vice versa | Done
|  |  | - Queue breaks | Ability for a user to pause in queue for break | Dropped
|  | On call support | - call budging, listening and/or whispering | Ability to have and perform the listed options for assistance and/or QA during call | Not Done
|  | IVR | - IVR configurations and provisions | Ability to add IVR audio to the system and reflect on inbound calls | Not Tested
|  | Listing | - Call lists shall be listed with filters available for a user to search | When a user searches/filters the cal list, it should return relevant results based on the selected parameter fields | Ongoing |  | - Work on list filters - provide an exit button for the filter form
| Quality Assessment | QA Form | - QA form with respective fields and saving | Have a form for relevant QA fields which can be submitted and saves awarded points | Done
|  |  | - Qa form having audio player for the respective call record with controls | The QA form that pops for a call should have an audio player that plays the respective relevant audio upon loading. It should have controls for pausing and rewinding | Done
|  |  | - Listing should allow supervisor to search for a particular call | Being able to filter call listing for QA to find a relevant call for analysis | Done |  | - Filter not available or not working
|  | QA Results | - Results from a quality analysis | One should be able to view the results of a QA as submitted by a supervisor | Done
| User Management |  | - User creation | User can be created and s/he can login successfully | Done
|  |  | - User update | User details can be updated relevantly | Done
|  |  | - Users levels/role separation - Administrator - Partner - Case Manager - Case Worker - Counsellor - Supervisor | - The user levels exist within the system and available during user creation | Done |  | - Add partner to the levels and test
|  | Password Management | - Change personal password | Each logged-in user can change their own password | Not Done
|  |  | - Change user password for administrators | Administrators can reset user password | Done
|  | Roles/Permissions | - Different user roles and role separation within the system as defined | - The different user roles to have distinctive role &separation | Done
|  | User Presence | - a report of system users, their current status and respective statistics | A supervisor should view the status of currently logged in users and their queue & activity status | Not Done |  | - Add to supervisor and Administrator account
| Dashboards | User Dashboards | - Dashboards relevant to the different user roles | Every user level presents a dashboard with relevant user statistics and data to the role | Ongoing |  | - Users do not currently have call & case statistics - administrators should see statisticsforthe entire system
|  |  | - Dashboard statistics filtering | Can filter statistics based on different parameters such as timeframe | Ongoing
|  | Wall dashboard |  | Wall dashboard that shows center statistics and real time user activities | Not Done
| Web Online | Online Web Page | - A information page with details such as: - Helpline services - Helpline FAQs - An option to create case - General helpline statistics - Calls and cases by location, type (VAC/GBV), categories and date | Web page created with relevant information as defined in the requirements | Ongoing
|  | Online Case Form | - Web form with relevant fields | A case form on the web page with the defined fields | Not Done
|  |  | - Ability to create a case successfully | Web online form can submit a case to the system | Not Done
|  |  | - web created cased listing on the CRM | The submitted cases from web online form are listed on the local system | Not Tested
|  |  | - Creating a system case with a web online listing | The case from web online can be used to create a case on the system | Not Tested
| Notifications | Case Update | - Users notified on case updates | Users who have interacted with a case receive notification when the case is updated | Ongoing |  | - Not received notifications on case update though there is a notification tab
|  | SMS | - Users notified on new/unread SMS | Users get a notification on an incoming SMS | Not Tested
|  | Email | - Users notified on new/unread emails | Users get a notification on an incoming Email | Not Tested
| Reporting | Comprehensive | - report lists with filters for different fields on the different system items, e.g calls, cases and performance | Show different item list reports such as cases and calls. The list report can be filtered based on relevant report parameters | Ongoing |  | - Some report filters are not fully working - Need for additional fields on some report filters
|  |  | - The list reports should be exportable in formats such as CSV, xlsx or pdf | Can export the different report list to a portable format such as CSV/XLSX/XLS or pdf | Ongoing |  | - Need for additional formats such as XLS/XLSX/PDF
|  | Pivot | - Custom pivoted reports for both calls and cases having graphical and statistical representaion. | Can do custom pivot reports | Done

## Phase II
UCHL VAC/GBV Upgrade System Feature Sign-Off Checklist
Module | Module | Item | Expected Results | Expected Results | Status | Status By | Status Comment | Priority
Phase II
| Integrations Channels | NSR | - Being able to push cases to National Single Registry | The system can push registered cases to National Singe Registry successfully | Not Tested
|  | SafePal | - Being able to accept cases from SafePal | The system can receive cases from SafePal and users can view and/or create system cases from them | Not Tested
|  | out | Posting cases to NGBVD | System can post registered cases to National Gender Based Violence Database | Not Tested
| Additional Sources | SMS | - being able to receive SMS | System can receive SMS as provided | Not Tested
|  |  | - being able to send SMS | Should be able to send SMS as provided | Not Tested |  |  |  | Done
|  |  | - being able to create a case with SMS thread | Creating a case based on an inbound SMS | Not Tested |  |  |  | Ongoing
|  | Email | - being able to receive Email | System can receive Email as provided | Not Tested |  |  |  | Not Tested
|  |  | - being able to send Email | Should be able to send Email as provided | Not Tested |  |  |  | Pending
|  |  | - being able to create a case with Email thread | Creating a case based on an inbound Email | Not Tested |  |  |  | Not Done
|  | Facebook | - being able to receive and view facebook feeds and/or chat | Streaming of Facebook feeds/chat within the application | Not Tested
|  |  | - Reply to facebook feeds and/or chats | Reply to respective facebook feeds/chats within the application | Not Tested |  |  |  | Dropped
|  |  | -Create a case with facebook feeds and/or chats | Use the listed facebook feeds/chats to create a case | Not Tested
|  | Twitter | - being able to receive and view tweets and/or chat | Streaming of tweets within the application | Not Tested
|  |  | - Reply to tweets and/or chats | Reply to respective tweets/chats within the application | Not Tested
|  |  | -Create a case with tweets and/or chats | Use the listed tweets/chats to create a case | Not Tested
|  | Whatsapp | - being able to receive Whatsapp messages | Can receive WhatsApp messages | Not Tested
|  |  | - being able to send message via Whatsapp | Can send messages via WhatsApp | Not Tested
|  |  | - being able to create a case from WhatsApp communication | Can create a case from WhatsApp communication/thread | Not Tested
|  | SafePal | - Ability to create a case from SafePal inbox cases | Creating a case from SafePal inbox cases | Not Tested
|  |  | - Receiving cases from SafePal | Can receive cases posted from SafePal | Not Tested
|  | Web Page | - Receive cases created online and list | Receiving cases from web online form | Not Tested
|  | Case Form | - Ability to create a case from listed cases from web online | Can create a system case from web online inbox messages/cases | Not Tested
| Mobile Application | Authentication | - Users can login and logout of the application | User can login and logout of the mobile application | Not Tested
|  | Cases | - Users can view relevant case menu items (New Cases, Escalated/Assigned Cases) | Users can view and update cases within the mobile application | Not Tested
|  |  | - Users can successfully create a case in the system through the mobile application | Users can successfully create a case from the mobile application and be listed within the system | Not Tested
|  | Offline Capability | - Users can still access the applicaton and cases even when there is not internet connection | Users have access to the application even without internet | Not Tested
|  |  | - Cases can be created while the device is offline and synchronize once online | Cases created while off internet are synchronized to the system once internet connection is available | Not Tested

## Sheet1
Item | Expected Results | Expected Results | Status | Status By | Status Comment
Login Process | - Can login successfully - Warnings on wrong credentials | Being able to login and receive error messages if the login is not successful | Not Tested
| - redirection to the right dashboard and role | Every user logged in should be redirected to the respective dashboard with details filtered per user level | Not Tested
Case creation | - Capture necessary fields for respective groupings in the case Capture form | All the fields for case form should be listed as per the FRD | Not Tested |  |  | Done
| - case form logic and flow | Step by step capture of case details from case reporter to case closure | Not Tested |  |  | Ongoing
| - Type options such as New Case, Follow Up, Service and Information inquiry | Being able to select reason for calling as either Follow Up, Service, Information Inquiry or New Case | Not Tested |  |  | Not Tested
Case edit | - Being able to edit a case with respective logic in mind | Ability to update case | Not Tested |  |  | Pending
Case View | - Segregate cases in groupings such as New, Escalated and/or All Cases - View individual cases with a printable version or exportable to PDF | View individual case with all the captured details | Not Tested |  |  | Not Done
| - provide filters for case list to allow for ease in case search | Search and/or filter a cases by different fields | Not Tested
| - Individual case view to have edit and printable where possible | Viewed case to have an option to edit | Not Tested |  |  | Dropped
Case escalation and assignment | - Counsellors and supervisors being able to escalate cases and view where possible | A case can be escalated by a counsellor and supervisor | Not Tested
| - case managers being able to assign a case to case workers - Define escalation matrix based on current logged in user | Assign/assign case to Case Workers by Case Managers | Not Tested
| Users can view listing of cases escalated to them and/or the cases they escalate to other users | Can view cases escalated in/out | Not Tested
Case identification | - Every case should have a unique case number | Cases created to have a unique case number to identify it. | Not Tested
| - Every case should have a source | Each case is tagged to a source | Not Tested
Case Trail | - maintain a history of case edits | Keep current record and keep the previous details upon case edit | Not Tested
Escalation matrix | - A case can be escalated in the following steps: Counsellor => Supervisor => Case Manager => Case Worker | Counsellor, Supervisor and Caseworker can escalate a case to the next user level | Not Tested
Case/call Disposition | - A case/call disposition available all through a call/case capture | Can dispose a case at any level and record the reason for disposing the case. | Not Tested
Information Inquiry | Form and data capture | - View information of importance in responding to client queries | Not Tested
| Update on FAQs | Create new questions for FAQs | Not Tested
Counselling | Form and data capture | - capture end to end information on counselling as offered to a client | Not Tested
SIP Phone setup & configuration | - SIP setup | Having a setup for SIP phone to receive and make calls | Not Tested
| - Inbound calls | Being able to receive calls on a SIP phone | Not Tested
| - SIP to SIP calls | Ability to make calls between registered system users | Not Tested
| - SIP Extension management | Assigning extension numbers to users | Not Tested
| - Form popup on call received | Case form should pop for external inbound calls upon receiving | Not Tested
| - Call transfer | One is able to transfer a call to another registered user | Not Tested
Call Queue Management | - Join and leave queue | A user can join and leave queue. One should not receive calls when not in queue and vice versa | Not Tested
| - Queue breaks | Ability for a user to pause in queue for break | Not Tested
On call support | - call budging, listening and/or whispering | Ability to have and perform the listed options for assistance and/or QA during call | Not Tested
IVR | - IVR configurations and provisions | Ability to add IVR audio to the system and reflect on inbound calls | Not Tested
Listing | - Call lists shall be listed with filters available for a user to search | When a user searches/filters the case list, it should return relevant results based on the selected parameter fields | Not Tested
Not Tested
QA Form | - QA form with respective fields and saving | Have a form for relevant QA fields which can be submitted and saves awarded points | Not Tested
| - Qa form having audio player for the respective call record with controls | The QA form that pops for a call should have an audio player that plays the respective relevant audio upon loading. It should have controls for pausing and rewinding | Not Tested
| - Listing should allow supervisor to search for a particular call | Being able to filter call listing for QA to find a relevant call for analysis | Not Tested
QA Results | - Results from a quality analysis | One should be able to view the results of a QA as submitted by a supervisor | Not Tested
Not Tested
| - User creation | User can be created and s/he can login successfully | Not Tested
| - User update | User details can be updated relevantly | Not Tested
| - Users levels/role separation - Administrator - Partner - Case Manager - Case Worker - Counsellor - Supervisor | - The user levels exist within the system and available during user creation | Not Tested
Password Management | - Change personal password | Each logged-in user can change their own password | Not Tested
| - Change user password for administrators | Administrators can reset user password | Not Tested
Roles/Permissions | - Different user roles and role separation within the system as defined | - The different user roles to have distinctive role &separation | Not Tested
User Presence | - a report of system users, their current status and respective statistics | A supervisor should view the status of currently logged in users and their queue & activity status | Not Tested
NSR | - Being able to push cases to National Single Registry | The system can push registered cases to National Singe Registry successfully | Not Tested
SafePal | - Being able to accept cases from SafePal | The system can receive cases from SafePal and users can view and/or create system cases from them | Not Tested
NGBVD | Posting cases to NGBVD | System can post registered cases to National Gender Based Violence Database | Not Tested
Not Tested
SMS | - being able to receive SMS | System can receive SMS as provided | Not Tested
| - being able to send SMS | Should be able to send SMS as provided | Not Tested
| - being able to create a case with SMS thread | Creating a case based on an inbound SMS | Not Tested
Email | - being able to receive Email | System can receive Email as provided | Not Tested
| - being able to send Email | Should be able to send Email as provided | Not Tested
| - being able to create a case with Email thread | Creating a case based on an inbound Email | Not Tested
Facebook | - being able to receive and view facebook feeds and/or chat | Streaming of Facebook feeds/chat within the application | Not Tested
| - Reply to facebook feeds and/or chats | Reply to respective facebook feeds/chats within the application | Not Tested
| -Create a case with facebook feeds and/or chats | Use the listed facebook feeds/chats to create a case | Not Tested
Twitter | - being able to receive and view tweets and/or chat | Streaming of tweets within the application | Not Tested
| - Reply to tweets and/or chats | Reply to respective tweets/chats within the application | Not Tested
| -Create a case with tweets and/or chats | Use the listed tweets/chats to create a case | Not Tested
Whatsapp | - being able to receive Whatsapp messages | Can receive WhatsApp messages | Not Tested
| - being able to send message via Whatsapp | Can send messages via WhatsApp | Not Tested
| - being able to create a case from WhatsApp communication | Can create a case from WhatsApp communication/thread | Not Tested
SafePal | - Ability to create a case from SafePal inbox cases | Creating a case from SafePal inbox cases | Not Tested
| - Receiving cases from SafePal | Can receive cases posted from SafePal | Not Tested
Web Page | - Receive cases created online and list | Receiving cases from web online form | Not Tested
Case Form | - Ability to create a case from listed cases from web online | Can create a system case from web online inbox messages/cases | Not Tested
Comprehensive | - report lists with filters for different fields on the different system items, e.g calls, cases and performance | Show different item list reports such as cases and calls. The list report can be filtered based on relevant report parameters | Not Tested
| - The list reports should be exportable in formats such as CSV, xlsx or pdf | Can export the different report list to a portable format such as CSV/XLSX/XLS or pdf | Not Tested
Pivot | - Custom pivoted reports for both calls and cases having graphical and statistical representaion. | Can do custom pivot reports | Not Tested
User Dashboards | - Dashboards relevant to the different user roles | Every user level presents a dashboard with relevant user statistics and data to the role | Not Tested
| - Dashboard statistics filtering | Can filter statistics based on different parameters such as timeframe | Not Tested
Wall dashboard |  | Wall dashboard that shows center statistics and real time user activities | Not Tested
Online Web Page | - A information page with details such as: - Helpline services - Helpline FAQs - An option to create case - General helpline statistics - Calls and cases by location, type (VAC/GBV), categories and date | Web page created with relevant information as defined in the requirements | Not Tested
Online Case Form | - Web form with relevant fields | A case form on the web page with the defined fields | Not Tested
| - Ability to create a case successfully | Web online form can submit a case to the system | Not Tested
| - web created cased listing on the CRM | The submitted cases from web online form are listed on the local system | Not Tested
| - Creating a system case with a web online listing | The case from web online can be used to create a case on the system | Not Tested
Case Update | - Users notified on case updates | Users who have interacted with a case receive notification when the case is updated | Not Tested
SMS | - Users notified on new/unread SMS | Users get a notification on an incoming SMS | Not Tested
Email | - Users notified on new/unread emails | Users get a notification on an incoming Email | Not Tested
Authentication | - Users can login and logout of the application | User can login and logout of the mobile application | Not Tested
Cases | - Users can view relevant case menu items (New Cases, Escalated/Assigned Cases) | Users can view and update cases within the mobile application | Not Tested
| - Users can successfully create a case in the system through the mobile application | Users can successfully create a case from the mobile application and be listed within the system | Not Tested
Offline Capability | - Users can still access the applicaton and cases even when there is not internet connection | Users have access to the application even without internet | Not Tested
| - Cases can be created while the device is offline and synchronize once online | Cases created while off internet are synchronized to the system once internet connection is available | Not Tested