## Sheet1
User Login | Login Process | - Can login successfully - Warnings on wrong credentials
- redirection to the right dashboard and role
Case Management | Case creation | Create a new case and save with all the details.The case should show the workflow.
Create a new case follow-up to update an existing case.
Create a New Inquiry Case
Create a New counselling Case
| Case edit | Edit case categroy & case Narative
| Case Seach | Search for cases with the filters provided
| Case escalation and assignment | Escalate case to the next level for further action ( social worker to supervisors, Supervisor to Case Manager , Case Manager to Case worker
| Case identification | Every Case has a Unique Number
| Case Trail | - maintain a history of case updates & Edits
| Case/call Disposition | - A case/call disposition available all through a call/case capture
Information Inquiry/Service Forms | Information Inquiry | Form and data capture
Update on FAQs
| Counselling | Form and data capture
Call Management | SIP Phone setup & configuration | - SIP setup
- Inbound calls
|  | - SIP Extension management | Automate the numbering
- Form popup on call received
- Call transfer/conference/invite
| Call Queue Management | - Join and leave queue
- Queue breaks
| On call support | - call budging, listening and/or whispering
| IVR | - IVR configurations and provisions
| Listing | - Call lists shall be listed with filters available for a user to search | - Work on list filters - provide an exit button for the filter form
Quality Assessment | QA Form | - QA form with respective fields and saving
- Qa form having audio player for the respective call record with controls
|  | - Listing should allow supervisor to search for a particular call | - Filter not available or not working
| QA Results | - Results from a quality analysis
User Management |  | - User creation
- User update
|  | - Users levels/role separation - Administrator - Partner - Case Manager - Case Worker - Counsellor - Supervisor | - Add partner to the levels and test
| Password Management | - Change personal password
- Change user password for administrators
| Roles/Permissions | - Different user roles and role separation within the system as defined
| User Presence | - a report of system users, their current status and respective statistics | - Add to supervisor and Administrator account
Dashboards | User Dashboards | - Dashboards relevant to the different user roles | - Users do not currently have call & case statistics - administrators should see statisticsforthe entire system
- Dashboard statistics filtering
Wall dashboard
Web Online | Online Web Page | - A information page with details such as: - Helpline services - Helpline FAQs - An option to create case - General helpline statistics - Calls and cases by location, type (VAC/GBV), categories and date
| Online Case Form | - Web form with relevant fields
- Ability to create a case successfully
- web created cased listing on the CRM
- Creating a system case with a web online listing
Notifications | Call Notifications | User can initiate the case process from notification | - Not received notifications on case update though there is a notification tab
| SMS | - Users notified on new/unread SMS
| Email | - Users notified on new/unread emails
Reporting | Comprehensive | - report lists with filters for different fields on the different system items, e.g calls, cases and performance | - Some report filters are not fully working - Need for additional fields on some report filters
|  | - The list reports should be exportable in formats such as CSV, xlsx or pdf | - Need for additional formats such as XLS/XLSX/PDF
| Pivot | - Custom pivoted reports for both calls and cases having graphical and statistical representaion. | =A2:F57